## Remediation Tracker
Finding ID | Finding Title | Source Framework | Related Risk | Severity | Status | Owner | Target Date | Closed Date | Notes
F-001 | Privileged access quarterly review not completed | ISO 27001 - 5.18 / 8.2 | RR-001 | Critical | Overdue | IAM Team | 28-Feb-2026 |  | Access review for 312 privileged accounts not performed on schedule
F-002 | Payment API security hardening pending pen test | ISO 27001 - 8.29 / PCI-DSS Req 6 | RR-002 | Critical | Overdue | API Security Team | 15-Mar-2026 |  | External pen test not yet commissioned despite Feb-2026 deadline
F-003 | Ransomware response playbook not tested | ISO 27001 - 5.26 / BCP | RR-003 | High | Overdue | CISO | 28-Feb-2026 |  | Tabletop exercise planned but not executed
F-004 | PDPPL cross-border transfer mechanism not established | PDPPL Art. 19 | RR-007 | Critical | Overdue | DPO | 31-Jan-2026 |  | DataSync Analytics transferring data to EU without lawful mechanism
F-005 | Vendor security contract clauses not updated for 5 suppliers | ISO 27001 - 5.20 | RR-007 | High | Overdue | Legal | 28-Feb-2026 |  | Legacy contracts missing PDPPL and security annexes
F-006 | DLP endpoint agent deployment incomplete | ISO 27001 - 8.12 | RR-004 | High | In Progress | SOC Team | 30-Apr-2026 |  | Deployed on 68% of endpoints; remaining in testing
F-007 | SIEM log source coverage below 90% target | ISO 27001 - 8.15 | RR-009 | High | In Progress | SOC Team | 30-Apr-2026 |  | Currently 74%; 8 log sources onboarding
F-008 | Mobile app OWASP pen test not completed | ISO 27001 - 8.25 | RR-010 | High | In Progress | App Dev Team | 31-May-2026 |  | Vendor selected; test scheduled 15-May-2026
F-009 | Critical patch compliance below 90% threshold | ISO 27001 - 8.8 | RR-008 | High | In Progress | IT Operations | 30-Apr-2026 |  | Currently 78%; patching sprint underway
F-010 | BEC dual-approval controls not fully enforced | ISO 27001 - 5.17 | RR-011 | Medium | In Progress | Finance & IT | 31-May-2026 |  | Finance approval workflow being updated in ERP
F-011 | CMDB incomplete - software asset inventory | ISO 27001 - 5.9 | RR-022 | Medium | In Progress | IT Operations | 30-Apr-2026 |  | SAM tool deployed; data ingestion 78% complete
F-012 | Media disposal procedure not formalised | ISO 27001 - 7.14 | RR-016 | Medium | In Progress | IT Operations | 31-May-2026 |  | NIST 800-88 procedure being documented
F-013 | DPIA register - 3 of 5 required DPIAs outstanding | PDPPL Art. 22 |  | Medium | In Progress | DPO | 31-May-2026 |  | DPIAs for analytics and payments being drafted
F-014 | Remote work security policy overdue for review | ISO 27001 - 6.7 |  | Medium | In Progress | HR & IT | 30-Apr-2026 |  | Policy last reviewed 2024; hybrid work changes required
F-015 | Data centre physical access upgrade | ISO 27001 - 7.2 | RR-012 | High | Closed | Facilities | 31-Jan-2026 | 15-Jan-2026 | Turnstile and biometric upgrade completed
F-016 | Cloud misconfiguration - public S3/blob buckets | ISO 27001 - 5.23 | RR-014 | High | Closed | Cloud Team | 28-Feb-2026 | 10-Feb-2026 | CSPM tool deployed; all buckets private
F-017 | MDM enrolment below 95% target | ISO 27001 - 7.9 | RR-015 | Medium | Closed | IT Operations | 31-Jan-2026 | 20-Jan-2026 | 99% enrolment achieved
F-018 | Password policy non-compliant with NIST SP 800-63B | ISO 27001 - 5.17 |  | Medium | Closed | IAM Team | 31-Jan-2026 | 12-Jan-2026 | Policy updated and enforced in AD
F-019 | Security awareness training completion below 85% | ISO 27001 - 6.3 |  | Medium | Closed | HR | 31-Jan-2026 | 20-Jan-2026 | 89% completion achieved
F-020 | Legacy SSL/TLS 1.1 not disabled on web services | PCI-DSS Req 4 |  | High | Closed | IT Operations | 31-Jan-2026 | 08-Jan-2026 | TLS 1.0/1.1 disabled; TLS 1.3 enforced
F-021 | Admin accounts sharing credentials on payment systems | PCI-DSS Req 8 | RR-001 | Critical | Closed | IAM Team | 15-Jan-2026 | 10-Jan-2026 | Unique accounts enforced; PAM tool deployed
F-022 | Backup recovery test not performed in 2025 | ISO 27001 - 8.13 |  | High | Closed | IT Operations | 31-Jan-2026 | 22-Jan-2026 | Recovery test passed; 4hr RTO confirmed
F-023 | Incident response plan not reviewed since 2023 | ISO 27001 - 5.24 |  | Medium | Closed | CISO | 31-Jan-2026 | 15-Jan-2026 | IRP v2.3 approved and tabletop tested
F-024 | Visitor log not maintained in IT areas | ISO 27001 - 7.2 | RR-019 | Low | Closed | Facilities | 31-Jan-2026 | 18-Jan-2026 | Digital visitor management system deployed
F-025 | Firewall rule review overdue by 6 months | ISO 27001 - 8.20 |  | Medium | Closed | Network Team | 31-Jan-2026 | 25-Jan-2026 | 154 rules reviewed; 23 removed
F-026 | No documented network architecture diagram | ISO 27001 - 8.22 |  | Low | Closed | Network Team | 31-Jan-2026 | 20-Jan-2026 | Network diagram v3.1 completed
F-027 | Procurement process missing security checklist | ISO 27001 - 5.19 |  | Medium | Closed | Vendor Mgmt | 28-Feb-2026 | 05-Feb-2026 | Vendor security checklist added to procurement
F-028 | CCTV retention policy not documented | ISO 27001 - 7.4 |  | Low | Closed | Facilities | 31-Jan-2026 | 15-Jan-2026 | 90-day retention policy documented
F-029 | Software licence audit not performed in 12 months | ISO 27001 - 5.32 |  | Low | Closed | IT Operations | 28-Feb-2026 | 01-Feb-2026 | SAM audit complete; 3 unlicensed packages removed
F-030 | DPO appointment not formally documented | PDPPL Art. 23 |  | High | Closed | CEO | 15-Jan-2026 | 10-Jan-2026 | DPO appointment letter and charter signed
F-031 | Privacy policy outdated - last updated 2023 | PDPPL Art. 5 |  | Medium | Closed | DPO | 28-Feb-2026 | 10-Feb-2026 | Privacy policy v1.2 published on website
F-032 | Employee screening policy missing background check detail | ISO 27001 - 6.1 |  | Low | Closed | HR | 28-Feb-2026 | 15-Feb-2026 | Screening policy v2.0 updated

## Summary
Status | Count
Overdue | 5
Open | 0
In Progress | 9
Closed | 18
Total | 32